## Sheet1
ID | Theme | Role | Story | Notes | Effort | Priority | Sprint
1 | Research and Information Gathering | Product Manager(Team Collabration in this case) | As a PM(Team Members), I/We want to conduct research and gather information related to develop auto movie ticket booking system when a booking opens for a movie. | Collect relevant data and insights to inform project planning. | 3 | High | Sprint 0
2 | Setup | Integration Engineer | As a integration engineer, I want to set up the client and server. | Ensure proper configuration of client and server. | 3 | High | Sprint 1
3 | Endpoint Creation | Frontend Developer | As a frontend developer, I want to create GET endpoints to fetch lists of cities, movies, and cinemas. | Implement API endpoints for data retrieval. | 5 | High | Sprint 2
4 | Form Creation | Developer | As a developer, I want to create a form on the client side with fields for inputting movie preferences. | Form fields: movie selection, seating preferences, etc. | 5 | High
5 | Data Storage | Database Developer | As a database developer, I want to save user preferences in the database when the form is submitted. | Implement backend logic for data persistence. | 5 | High | Sprint 3
6 | Ticket Selection | Developer | As a developer, I want the server to poll the BookMyShow website and select seats based on user preferences. | Develop automated process for ticket selection. | 13 | High
7 | Ticket Reservation | Developer and Integration Engineer | As a developer and integration engineer, I want the system to reserve tickets according to user preferences and send an email confirmation. | Implement email notification for ticket reservations. | 5 | High | Sprint 4
8 | Preferences Clearing | Developer | As a developer, I want the system to clear user preferences after completing a ticket reservation. | Ensure user preferences are reset after each booking. | 5 | Medium
9 | Integration Testing | QA Engineer | As a QA engineer, I want to perform integration and chaos testing to ensure system stability and reliability. | Conduct thorough testing to identify and resolve issues. | 8 | Medium